## Sheet1
Leeds Raspberry Jam YISC Entry | BOM
Item: | Cost: | Qty: | Source: | Total Cost: | Notes: | Estimated Arrival | Ordered: | Shipped: | Tracking:
Control PCB x 5 | 1.57 | 1 | JLCPCB | 1.57 | Ideally needs ordering as soon as possible, custom made and takes 2-3 months to arrive. | Late July | Ordered 31/5/19 | 2019-06-02 | GN013116413GB
Shipping | 4.78 | 1 | JLCPCB | 4.78 |  |  | Ordered 31/5/19
Power Supply | 0.31 | 5 | AliExpress | 1.55 |  | Mid June | Ordered 31/5/19 | 2019-06-01 | UR517193842CN
Shipping | 2.31 | 1 | AliExpress | 2.31 |  |  | Ordered 31/5/19
ESP8266 CPU | 0.96 | 5 | AliExpress | 4.8 | Includes one spare processor incase we mess up the programming and brick one | Mid June | Ordered 31/5/19
Shipping | 2.3 | 1 | AliExpress | 2.3 |  |  | Ordered 31/5/19
Relays | 1.47 | 1 | AliExpress | 1.47 |  | Mid June | Ordered 31/5/19
CH340Gs | 1.2 | 1 | AliExpress | 1.2 |  | Mid June | Ordered 31/5/19
12mHZ Crystals | 0.81 | 1 | AliExpress | 0.81 |  | Mid June | Ordered 31/5/19
LD1117V33 | 1.93 | 1 | AliExpress | 1.93 |  | Mid June | Ordered 31/5/19
22pF Caps | 0.79 | 1 | AliExpress | 0.79 |  | Mid June | Ordered 31/5/19
100nF Caps | 0.79 | 1 | AliExpress | 0.79 |  | Mid June | Ordered 31/5/19
MCP3008 | 1.59 | 1 | AliExpress | 1.59 |  | Mid June | Ordered 31/5/19
10uF Caps | 0.76 | 1 | AliExpress | 0.76 |  | Mid June | Ordered 31/5/19
Shipping | 1.1 | 1 | AliExpress | 1.1 |  | Mid June | Ordered 31/5/19
MicroUSB Boards | 0.32 | 1 | AliExpress | 0.32 |  | Mid June | Ordered 31/5/19 | 2019-06-01 | UR517194627CN
Shipping | 0.89 | 1 | AliExpress | 0.89 |  | Mid June | Ordered 31/5/19
Potentiometers | 0.79 | 1 | AliExpress | 0.79 |  | Mid June | Ordered 31/5/19
Knobs | 0.59 | 1 | AliExpress | 0.59 |  | Mid June | Ordered 31/5/19
Shipping | 1.51 | 1 | AliExpress | 1.51 |  | Mid June | Ordered 31/5/19
3D Printed Enclosures | 0 | 4 | Matt M (thanks!) | 0 | Three for the ESP8266 units and one for the pi/potentiometer unit. | ??
Lamps/appliances to test with | 0 | 3 | Matthew C | 0 | Already have some.. | N/A
2M Extension Lead PL09165 | 4.14 | 1 | CPC | 4.14 | For wiring inside the appliance units + socket and plug for one of the appliance units. | 3-5 days after order | Ordered 31/5/19
Fuse holder FF01945 | 0.98 | 3 | CPC | 2.94 |  | 3-5 days after order | Ordered 31/5/19
10A fuse (10 pack) FF03151 | 1.75 | 1 | CPC | 1.75 |  | 3-5 days after order | Ordered 31/5/19
|  | Total: |  | 40.68